## Summary
Row Labels | Count of Custom field (Severity)
Blocker | 24
Critical | 32
Major | 87
Minor | 13
Grand Total | 156

## 1. service issues
JiRA ID | Raised by | Intimated date | resolution date | Issue Description | Resolution provided | Issue root cause | Time taken
TTVS-16298 | Shashikiran CR | 2023-10-31 | 2023-10-31 | Tracelink generated xml files are not uploading | Guided him how to create multiple tracelink for separate business partners and how to generate and upload specific tracelink xml files | Lack of knowledge on multiple tracelink. | 4 hrs
TTVS-16265 | Himanshu patel | 2023-10-31 | 2023-10-01 | wrong EPC URN ID format got formed for SSCC <epc>urn:epc:id:sgtin:0380830.023292.3000000730</epc> <epc>urn:epc:id:sscc:003701213001409069</epc> <epc>urn:epc:id:sgtin:0380830.023292.3000000809</epc> The loose shipper serial number-003701213001409069 with sample status. poid-13 lot number-AH230042 | It is not a BUG. it is an Invalid operation/ Human error. Kindly note that: The Subject, which is selected in PO for getting SSCC number, the same Subject should be selected while creating SO. Otherwise, application won't able to bifurcate the SSCC number for creating urn:epic:id:sscc for e.g. 1. create a 2L po with US HDA 2017 2. select subject - XYZ for shipper station. 3. Run and close the PO. 4. Now create a new SO and select subject -XYZ itself. | Invalid operation/Human Error | 4hrs
NA | SelvaKumar |  |  | Tracelink is not available in Serial Number provider list at Abhilas | Harishankar implemented data correction from Backend and resolved the issue | Since Tracelink was not provided to this customer earlier it was not coded in custom script. Also, No one from QA or service team conveyed this to Developer before releasing custom script. | 2hrs
TTVS-18226 | Pardeep | 2024-02-12 | 2024-02-16 | MIP belarus- Sequence start is too big for defined template, error pop up at time of utilization report upload for CRPT Turon | fix provided by ajeet and released on site by me | This issue was due to foreign key constraint and after discussion within team, we concluded that this constraint is not required and should be removed to resolve this issue. Patch released | 5 days
TTVS-21927 | Bupesh | 2024-06-11 | 2024-02-20 | PSK Russia - Extra tags are observed in report 415 XML file. while User recalled report 415 and Re-generated 415 | Fix provided by dev | Error Handling done for showing data for just current move_order_415 message by adding extra filter. | 8 days

## 2. Projects
Sr. No. | Project Name | QA Deadline | Released On | Remark
1 | Uzbek - serial & aggre | 2023-04-28 | 2023-04-25 | before time
2 | Apnar Pharma | Delayed from customer | 2023-06-02 | before time
3 | KSP cum Medpharma | 2023-06-20 | Medpharma - 19-06-2023 KSP - 16-06-2023 | before time
4 | JPM Jordan | 2023-06-23 | 2023-06-22 | before time
5 | Fremed | NA | 2023-07-04 | On-time
6 | Lyne Labs | Delayed from customer | 2023-08-26 | On-time
7 | Harman Arvato | 2023-09-29 | 2023-09-29 | On-time
8 | Archiving Purging | NA | 2023-10-28 | On-time
9 | Belcher - Covetrus, Ace & Kaiser integration | Delayed from customer | 2023-12-19 | On-time
10 | Novitium - data Migration - Tracelink release | 2024-01-12 | 2024-01-17 | 3 days delay
11 | MIP- CRPT TURON | 2024-01-29 | 2024-01-26 | before time
12 | Carnegie | 2024-03-08 | 2024-03-07 | before time
13 | M/S LekPharm | 2024-04-18 | 2024-04-22 | 4 days delay
14 | Avvarus - Russia nutra phase 3 +crypto exp + online util reporting | 2024-05-06 | 2024-05-07 | 1 day delay
15 | Avvarus - Kyrgyzstan regulatory | 2024-05-06 | 2024-04-26 | before time
16 | Zydus Hospira Phase02 SAP ICH SFTP 13 regulatories | 2024-05-31 | 2024-05-31 | On-time
17 | WinmMedicare | 2024-06-28 | 2024-06-15 | before time
18 | Avvarus - EU Aggregation custom 7 | NA | 2024-08-02 | On-time
19 | Avvarus - Softgroup Integration | NA | 2024-08-02 | On-time
20 | Avvarus - Quickpharm Integration | NA | 2024-08-02 | On-time

## Sheet1
Row Labels | Count of Remark
3 days delay | 1
before time | 6
On-time | 5
Grand Total | 12